## Stakeholder Engagement Matrix
Stakeholder | Unaware | Resistant | Neutral | Supportive | Leading | How?
Users | C |  |  | D |  | Raise awareness through marketing campaigns
Partners/Shops sales staff |  | C | D |  |  | Resistance to change may be solved by workshops or training on how to use the new system
Shops marketing representatives |  |  | C | D |  | Conduct seminars on how subscriptions, discounts & promotions will enhance marketing
Project sponsor |  |  |  | C | D | Through cooperation, collaboration, and excellent communication
UI Designer |  |  | C | D
App developer |  | C |  | D
Back-end developer |  |  | C, D
Information architect |  |  | C, D
Content producer |  | C | D
Project manager |  |  |  |  | C,D
Discount card company |  |  |  | C | D | Emphasizing on the benefits and customer loyalty resulting
Customer service department |  | C |  | D |  | Train them with the most common issues faced by users
C: Current
D: Desired

## Communications Mgmt Plan
Purpose | Stakeholder | Medium | Contents | Frequency
Marketing | Users | Emails | Ads, Newsletters | Bi-weekly
Preparation | Partners/Shops sales staff | Video Conferencing | Workshops | Monthly
Data Update | Shops marketing representatives | Phone | Promotions/Discounts updates | Bi-weekly
Team status | Project sponsor | Face-to-face/Emails | Ask for updates, work progress, remaining deliverables | two times/week
UI Designer
App developer
Back-end developer
Information architect
Content producer
Project manager
Project status | Discount card company | Face-to-face | Reporting progress | Monthly
Preparation | Customer service department | Video Conferencing | Training seminars | Monthly